# Response to the Husch Blackwell Report

Presented by Jane Cassidy, PhD, Interim Vice President

## Office Operations

### Accomplishments

- Interim Vice President hired

- Reporting lines changed

- Four positions advertised

- Director of Lighthouse full time

- Office moved to 118 Himes Hall

### Recommendations

- Recommendation #1 in progress

- Recommendation #2 in progress

- Recommendation #3 completed

- Recommendation #4 completed

### Title IX Organization Chart, March 16, 2021

- General Counsel
Winston Decuir, Jr.

  - Title IX Coordinator
Jennie Stewart

    - Lead Investigator
Jeff Scott

### Proposed Office of Civil Rights & Title IX Organization Chart, April 10, 2021

- Interim Vice President

  - Assistant to the Vice President

  - Title IX Coordinator 
(Linked reporting line to Director of Lighthouse Program, Susan Bareis. The Lighthouse Program Director reports to Interim Executive Director of Student Health Center, Julie Hupperich)

    - Deputy Title IX Coordinator for Prevention and Training

    - Case Manager

    - Lead Investigator, Jeff Scott

    - Investigator

  - ADA and Accessibility Coordinator

    - Director of Digital Resources & Content Accessibility

  - Civil Rights Coordinator

    - Case Manager

    - Investigator

  - Clery Coordinator

#### Projected Timeline: Operations

- Hire dates for Assistant to the Vice President, Case Manager, and Investigators:  May 20

- Hire date for Title IX Coordinator: July 15

- Hire date for Vice President: January 1, 2022

## Process

### Accomplishments

- Timeline established for discrimination cases

- Process for complaint if process not handled promptly

- Restorative justice process currently in use

### Recommendations

- Recommendation #13 in progress

- Recommendation #14 in progress

- Recommendation #15 in progress

### Title IX Process and Timeline

- Complaint Received in Title IX Office

- 1 day - Title IX Coordinator or designee initiates contact with Complainant

- 3 business days -Title IX Coordinator or designee meets with Complainant

- 1 Business day - Determination made to proceed

- 1 business day - Notice of Allegations

- 30 business days - Investigation Process

- 30 business days - Review of Draft Report and Evidence

- 3 business days- Final Report Prepared

- 15 business days* - Prehearing Conference and Hearing

- 10 business days - Appeal

- 10 business days - Appeal Decision

*No pre-hearing or hearing may proceed earlier than 10 days post receipt of final report Informal Resolution

#### Projected Timeline: Process

- Formalize alternative resolution processes: August 15

- New Civil Rights and Title IX policy that will describe reporting process, define mandatory reporters, and provide sanctions for employees who fail to report: July 15

- Presumptively Appropriate Sanctions for students found responsible for sexual misconduct: July 15

## Training and Education

### Accomplishments

- All Athletics appointees required to make reports of sexual discrimination of students directly to the Title IX Coordinator

- Contract established between Athletics and STAR for education, training, and policy development

- Contract established between LSU and STAR for education, training, and review of current online training modules

- STAR has provided a first educational session on sexual misconduct to members of the LSU football team

- Bystander Intervention program implemented by Athletics

### Recommendations

- Recommendation   #7 in progress

- Recommendation #10 in progress

- Recommendation #12 in progress

#### Projected Timeline: Training and Education

- Annual mandatory training for employees, graduate assistants, and student workers reviewed by STAR, recommendations included in revisions, and implemented: August 15

- MyStudentBody training for new students reviewed by STAR, recommendations included in revision, and implemented: August 15

- Training for Title IX personnel: First week in June

## Record Keeping and Reporting

### Accomplishments

- MOU with LSU PD signed

- Assessments of Title IX training sessions implemented

### Recommendations

- Recommendation #5  in progress

- Recommendation #6 in progress

- Recommendation #9 completed

- Recommendation #17 in progress

#### Projected Timeline: Record keeping and reporting

- Format of quarterly reports being determined, and reports will be provided to the president every year on or before March 31, June 30, September 30, and December 30

- Format for annual reporting for campus being determined, and report will be published on September 1, 2021 and then annually on or before March 1

- Training in Maxient for all Title IX and Civil Rights employees and collaborators scheduled for May 24, 2021

- Assessment of Title IX responsiveness and satisfaction by all who use our services will go into effect June 1, 2021

## Communication and Accountability

### Accomplishments

- Easy to use and easy to locate website for reporting created www.lsu.edu/support

- Tracker has been developed and is being used/updated for all action items in the Husch Blackwell report; includes action item, responsible person/office, deadline, and updates on progress

- Clarity is being communicated to the campus community that all sexual misconduct by or toward students must be reported to the Title IX coordinator

### Recommendations

- Recommendation #8 in progress

- Recommendation #11 in progress

- Recommendation #16 in progress

- Recommendation #18 ongoing

#### Projected Timeline: Communication & Accountability

- New Civil Rights and Title IX policy that will describe reporting process, define mandatory reporters, and sanctions for employees who fail to report: July 15

- Navigate platform (EAB) used by students to schedule appointments on campus to include appointments with Office of Civil Rights & Title IX: May 15

- New App specifically for Civil Rights & Title IX developed by Communications & University Relations for campus community: July 1

- Tracker made available upon launch of new Title IX website: May 1

- New website for the Office of Civil Rights & Title IX: April 19 lsu.edu/civil-rights